## Sheet1
HDF Java Tools: To Do List | Bob | Peter | Mike
(April 1998)
(mcgrath@ncsa.uiuc.edu)
A. Ongoing Maintenance & Development:
1.Fix bugs as needed | 1A | 1A | 1A
2.Support and test on more platforms | 1B | 1A | 1B
*Need to work on Unix ports
3.Improved engineering, Modularize design | 1C/2B/3C | 2A | 2A
4.Incorporate new Java technology as available, e.g., |  | 3A | 3A
1.JDK 1.2, Java Foundation Classes (STILL IN BETA)
2.Java graphics support
5.The User’s Guide and other documentation needs wor | 1B/2B | 1B | 1B
B. Completed, we need user feedback
1.Plot features--many possible features
2.histograms of values
3.annotation of images
4.Create distribution packages that include needed libraries (HDF, Java,
HDF-EOS, etc)
C. Left over from previous list
1.Improved visualization and analysis features
1.Support for large images (i.e., too large for memory) | 1B/2B/3A | 1B/2A | 1B/2A
Frequent complaints, this is a fatal limitation for many users.
Needs much more work. (Also check Java 1.2 changes.)
2.image handling (i.e., from a multi-dimensional dataset, from a series of
images in a single file, and images from multiple files)
1.tiling from multiple image sources | 1A | 3B | 3B
3.Investigate animation for arrays with more than 3 dimensions |  | 1B | 3C
2.Generate minimal numerical analysis (min, max, value range/frequency, etc). | 1A | 1B | 1B
3.Extensibity so that users and third parties are be be able to add modules
* this probably is much more than just modularizing the code.... |  | 2A | 2B/3A
4.Provide a "clearing house" for contributed extensions | 1C | 3A | 3A
* Will do a report on the Alliance Repo
5.Display data attributes (metadata) in a structured, human readable format | 1A | 1A | 1A
(not just a raw dump).
*Need to get a clear specification of this
6.Load (read):
HDF |  | 1A | 1A
binary array data | 1C/2B | ? | 1A
ASCII array data | 1C/2B | 1A | 1A
HDF-EOS |  | 3B | 3B
7.Save (write) all or user defined subset of the data to: binary array data
ASCII array data | 1C/2B | 1A | 1A
HDF | 1C/2B | 1A | 1A
jpeg |  | 3B | 3B
gif |  | 3B | 3B
tiff/geotiff |  | 3B | 3B
net-CDF |  | 3C | 3C
postscript |  | 3B | 2B
HDF-EOS |  | 3B | 3B
8.Print images, plots, and data attributes. |  | 2B | 2B
9.Provide setting and saving preferences (Default load/save format, window |  | 2A | 2A
positions, views, etc)
D. Client/Server, Remote File Access / JHS
1.Access to remote files
1.Standard classes to access HDF files locally or remotely |  | 2A | 2A
Prototype DONE -- need to be finished -- see below
2.Experiment with candidate technologies, e.g.,
1.servlets YES
2.RMI NOT YET
* note: examine vizAd | 2B | 2B | 2B
3.Java Beans NOT YET
* note: examine Tango, etc., Alliance Grid stuff | 2B | 2A | 2A
4.Java/CORBA NOT YET |  | 2B | 2B
2.Improvements for remote file access: | 2A | 2A | 2A
need interface so that users can locate and access servers and files
need to document server set up (including Servlet version)
error handling, etc. for remote access
give feed back about what is happening on long transfers
create a "stop" button, time out on long transfers and ask "do you
want to continue?"
E. From the requested features list:
1.Cannot generate a spreadsheet from an SDS. In Collage, this |  | 1A | 1A
was the "native" depiction of SDSs.
2.There are too many image windows employed. Their purposes | 2B | 1B | 1B
are not very clear. Maybe some simple labels would make this
more understandable.
3.Spreadsheet shows numbers as if they were floats, regardless | 1C | 1A | 1A
of type. Since spreadsheets are always from raster images and
they are usually integers, this is a bit confusing/annoying.
4.Similarly, many of the higher level objects are represented as
folders. This makes obvious another level of hierarchy that is | 2B | 1B | 1B
hidden by the HDF interfaces. Maybe a different icon (instead
of a plain folder) for these compound or complex "objects"
would make things clearer here.
5.SDSs are displayed both as whole "objects" (as SDSs) and in |  | ?? | ??
their full gory detail (as collections of stuff under Vgroups).
Very confusing.
6.Field plots from Vdatas are nice, but adding some scaling |  | 2B | 2B
options would be good. I can think of three options:
group - all plots scaled together to fit the window
constrained group - all plots scaled according to one
user selected plot, which has been scaled to fit window.
individual - each plot scaled independently to fit window
(easier to see dynamic range of each field – check
DIAL plots)
7."Radial Plots" is a misnomer for non-polar images. | 1C | 1A | 1A
8.Vertical plots should be possible. |  | ?? | ??
9.When operations are performed on an un-zoomed image, no |  | 2B | 2B
effects are seen in the zoomed area. Either an update button or
a toggle for continuous update would be nice.
10.After loading a largish attribute, the cursor doesn’t revert to |  | 1A | 1A
normal until the mouse is clicked (it stays an hourglass).
11.The title of the tree panel reads "Hierarchy of the HDF."
Expanded, this would read "Hierarchy of the Hierarchical Data
Format." I think you really mean to say "Hierarchy of the HDF | 1A | 1A | 1A
file."
12.Feature request #137: Could JHV display the dimension | 1A | 2A | 2A
scale values rather than the pixel values, for raster grids, such
as when moving the mouse cursor over an image in the "Image
from HDF" dialog?
13.Feature request #156: Allow JHV to read in a palette |  | 2A | 2A
description.
14.Feature request, not numbered yet: Deal with Vdata |  | 2A | 2A
entries order > 1
Following is a response from the user regarding the order in a
vdata, and what JHV should show. I kind of agree with him.
Could we use a scroll bar, as he suggested, to view all the
values?
>The reason we would like to use jhv is to check the HDF files
that we write.
>Therefore, we would like to see all entries. By the way, what
is the point of
>fixing the maximum number of entries displayed to 3 in such a
highly dynamic
>language like java? If it doesn't fit in the window, you could
just put
>scrollbars around it.
15.Feature request from REMcG: Selecting subset:
Improve the selection of sub sets from browse images,
especially large and 3D SDSs. | 2B | 2A | 2A
show the precise dimensions of the bounding box
create an optional dialog box to select exact region, a la
DIAL/SDB.
F. Requested but not currently promised, or Deferred, Cancelled
1.Support for collaboration using the NCSA Habanero environment
Support JDK 1.02 final version
Port to Habanero 1.1 environment
Investigate Habanero Multicast support
Create consistent "look and feel" for regular and collaborative
versions
2.publicly available standard applets
3.Complete test suite
Investigate Java testing tools
Create standard Java testing methodology
4.Java Classes which understand HDF
NOT PLANNED EVER-- see WebWinds for limited Java classes
5.Ability to handle HDF-EOS data in a manner that uses the HDF-EOS
attributes/qualities.
Possible new project
6.HDF-EOS java wrapper or equivalent.
NASA or Hughes should do this....
7.Creating/Modifying/Merging/Editing HDF files
Possible new project
G. Wish List
1.HDF5 support?
2.Integrate with Horizon?
3.Integrate with Emerge?
4.Support Nancy's CGI?

## Sheet2
HDF Java Tools: To Do List | Bob | Peter | Mike
(April 1998)
(mcgrath@ncsa.uiuc.edu)
A. Ongoing Maintenance & Development:
1.Fix bugs as needed | 1A | 1A | 1A
2.Support and test on more platforms | 1B | 1A | 1B
*Need to work on Unix ports
3.Improved engineering, Modularize design | 1C/2B/3C | 2A | 2A
4.Incorporate new Java technology as available, e.g., |  | 3A | 3A
1.JDK 1.2, Java Foundation Classes (STILL IN BETA)
2.Java graphics support
5.The User’s Guide and other documentation needs wor | 1B/2B | 1B | 1B
B. Completed, we need user feedback
1.Plot features--many possible features
2.histograms of values
3.annotation of images
4.Create distribution packages that include needed libraries (HDF, Java,
HDF-EOS, etc)
C. Left over from previous list
1.Improved visualization and analysis features
1.Support for large images (i.e., too large for memory) | 1B/2B/3A | 1B/2A | 1B/2A
Frequent complaints, this is a fatal limitation for many users.
Needs much more work. (Also check Java 1.2 changes.)
2.image handling (i.e., from a multi-dimensional dataset, from a series of
images in a single file, and images from multiple files)
1.tiling from multiple image sources | 1A | 3B | 3B
3.Investigate animation for arrays with more than 3 dimensions |  | 1B | 3C
2.Generate minimal numerical analysis (min, max, value range/frequency, etc). | 1A | 1B | 1B
3.Extensibity so that users and third parties are be be able to add modules
* this probably is much more than just modularizing the code.... |  | 2A | 2B/3A
4.Provide a "clearing house" for contributed extensions | 1C | 3A | 3A
* Will do a report on the Alliance Repo
5.Display data attributes (metadata) in a structured, human readable format | 1A | 1A | 1A
(not just a raw dump).
*Need to get a clear specification of this
6.Load (read):
HDF |  | 1A | 1A
binary array data | 1C/2B | ? | 1A
ASCII array data | 1C/2B | 1A | 1A
HDF-EOS |  | 3B | 3B
7.Save (write) all or user defined subset of the data to: binary array data
ASCII array data | 1C/2B | 1A | 1A
HDF | 1C/2B | 1A | 1A
jpeg |  | 3B | 3B
gif |  | 3B | 3B
tiff/geotiff |  | 3B | 3B
net-CDF |  | 3C | 3C
postscript |  | 3B | 2B
HDF-EOS |  | 3B | 3B
8.Print images, plots, and data attributes. |  | 2B | 2B
9.Provide setting and saving preferences (Default load/save format, window |  | 2A | 2A
positions, views, etc)
D. Client/Server, Remote File Access / JHS
1.Access to remote files
1.Standard classes to access HDF files locally or remotely |  | 2A | 2A
Prototype DONE -- need to be finished -- see below
2.Experiment with candidate technologies, e.g.,
1.servlets YES
2.RMI NOT YET
* note: examine vizAd | 2B | 2B | 2B
3.Java Beans NOT YET
* note: examine Tango, etc., Alliance Grid stuff | 2B | 2A | 2A
4.Java/CORBA NOT YET |  | 2B | 2B
2.Improvements for remote file access: | 2A | 2A | 2A
need interface so that users can locate and access servers and files
need to document server set up (including Servlet version)
error handling, etc. for remote access
give feed back about what is happening on long transfers
create a "stop" button, time out on long transfers and ask "do you
want to continue?"
E. From the requested features list:
1.Cannot generate a spreadsheet from an SDS. In Collage, this |  | 1A | 1A
was the "native" depiction of SDSs.
2.There are too many image windows employed. Their purposes | 2B | 1B | 1B
are not very clear. Maybe some simple labels would make this
more understandable.
3.Spreadsheet shows numbers as if they were floats, regardless | 1C | 1A | 1A
of type. Since spreadsheets are always from raster images and
they are usually integers, this is a bit confusing/annoying.
4.Similarly, many of the higher level objects are represented as
folders. This makes obvious another level of hierarchy that is | 2B | 1B | 1B
hidden by the HDF interfaces. Maybe a different icon (instead
of a plain folder) for these compound or complex "objects"
would make things clearer here.
5.SDSs are displayed both as whole "objects" (as SDSs) and in |  | ?? | ??
their full gory detail (as collections of stuff under Vgroups).
Very confusing.
6.Field plots from Vdatas are nice, but adding some scaling |  | 2B | 2B
options would be good. I can think of three options:
group - all plots scaled together to fit the window
constrained group - all plots scaled according to one
user selected plot, which has been scaled to fit window.
individual - each plot scaled independently to fit window
(easier to see dynamic range of each field – check
DIAL plots)
7."Radial Plots" is a misnomer for non-polar images. | 1C | 1A | 1A
8.Vertical plots should be possible. |  | ?? | ??
9.When operations are performed on an un-zoomed image, no |  | 2B | 2B
effects are seen in the zoomed area. Either an update button or
a toggle for continuous update would be nice.
10.After loading a largish attribute, the cursor doesn’t revert to |  | 1A | 1A
normal until the mouse is clicked (it stays an hourglass).
11.The title of the tree panel reads "Hierarchy of the HDF."
Expanded, this would read "Hierarchy of the Hierarchical Data
Format." I think you really mean to say "Hierarchy of the HDF | 1A | 1A | 1A
file."
12.Feature request #137: Could JHV display the dimension | 1A | 2A | 2A
scale values rather than the pixel values, for raster grids, such
as when moving the mouse cursor over an image in the "Image
from HDF" dialog?
13.Feature request #156: Allow JHV to read in a palette |  | 2A | 2A
description.
14.Feature request, not numbered yet: Deal with Vdata |  | 2A | 2A
entries order > 1
Following is a response from the user regarding the order in a
vdata, and what JHV should show. I kind of agree with him.
Could we use a scroll bar, as he suggested, to view all the
values?
>The reason we would like to use jhv is to check the HDF files
that we write.
>Therefore, we would like to see all entries. By the way, what
is the point of
>fixing the maximum number of entries displayed to 3 in such a
highly dynamic
>language like java? If it doesn't fit in the window, you could
just put
>scrollbars around it.
15.Feature request from REMcG: Selecting subset:
Improve the selection of sub sets from browse images,
especially large and 3D SDSs. | 2B | 2A | 2A
show the precise dimensions of the bounding box
create an optional dialog box to select exact region, a la
DIAL/SDB.
F. Requested but not currently promised, or Deferred, Cancelled
1.Support for collaboration using the NCSA Habanero environment
Support JDK 1.02 final version
Port to Habanero 1.1 environment
Investigate Habanero Multicast support
Create consistent "look and feel" for regular and collaborative
versions
2.publicly available standard applets
3.Complete test suite
Investigate Java testing tools
Create standard Java testing methodology
4.Java Classes which understand HDF
NOT PLANNED EVER-- see WebWinds for limited Java classes
5.Ability to handle HDF-EOS data in a manner that uses the HDF-EOS
attributes/qualities.
Possible new project
6.HDF-EOS java wrapper or equivalent.
NASA or Hughes should do this....
7.Creating/Modifying/Merging/Editing HDF files
Possible new project
G. Wish List
1.HDF5 support?
2.Integrate with Horizon?
3.Integrate with Emerge?
4.Support Nancy's CGI?